## README
HMS R1 Requirements
Version 0.5, 28 Sep 2026
Sheets
R1 Requirements | One row per requirement, with Given, When, Then.
BR Coverage | Each business requirement mapped to requirement ids.
Decisions | Confirmed decisions and open questions.
Build Gaps | What is not yet built.
Counts
Total requirements | 107
Built+tested | 97
Not built | 2
R1b | 3
Built (UI or Edge Function work remains) | 4
Decision needed | 1
How to read a row
Given / When / Then | The acceptance criterion. A tester can run it as written.
Permissions | Permission keys checked by the database. Grant level Y, L (limit) or O (own).
Verified by | Test file number in supabase/tests. Run with supabase/tests/run.sh.
Built by | Database function or object that implements the requirement.

## R1 Requirements
ID | Module | Screens | Requirement | BR trace | Priority | Release | Permissions | Transition / rule refs | Given | When | Then | Built by | Verified by (tests) | Status
PLT-001 | Platform & Tenancy | (signup page) | A person with a confirmed email creates a hotel account in one step. | BR-001, BR-002 | Must | R1 | (any signed-in user) | Rule: Signup protection; A13 | a signed-in user with a confirmed email and no hotel | they submit business name, country and property name | a tenant, a 30-day trial, one property with country defaults, and the System Administrator and General Manager roles exist for them | create_hotel, provision_tenant | 10, 17 | Built+tested
PLT-002 | Platform & Tenancy | (signup page) | Signup is refused for an unconfirmed email and for a user who already belongs to a hotel. | BR-017 | Must | R1 | - | Rule: Signup protection | a user whose email is not confirmed | they try to create a hotel | the request is refused with E_EMAIL_UNVERIFIED; a user who already has a hotel gets E_ALREADY_HAS_HOTEL | create_hotel | 17 | Built+tested
PLT-003 | Platform & Tenancy | (all) | One hotel can never see or change another hotel's data. | BR-002, BR-017 | Must | R1 | - | Rule: Tenant isolation; A1 | two hotels with data | a user of hotel B queries or calls functions with hotel A's ids | no rows come back, writes are refused, and functions answer E_PERM or E_NOT_FOUND | row-level security on every table; tenant_id on every row | 11, 16 | Built+tested
PLT-004 | Platform & Tenancy | (signup page), SET-01 | A new property is seeded from its country template (currency, timezone, tax lines, payment methods, charge codes). | BR-002 | Must | R1 | - | Rule: Country templates; A10, A11 | a hotel signs up in Nigeria | the property is created | it uses naira and Africa/Lagos with service charge, VAT 7.5% and a state levy line at 0%, all marked unverified; other countries get no guessed taxes | seed_property_defaults, country_templates | 17 | Built+tested
PLT-005 | Platform & Tenancy | (banner) | A trial ends automatically and the hotel becomes read-only. | BR-001 | Must | R1 | - | Rule: Read-only tenants; A13 | a hotel whose trial end date has passed | the daily clock runs | the subscription is Expired, the change is in the subscription history, and the hotel can read but not create | run_subscription_clock, assert_writable, tenant_writable | 15 | Built+tested
PLT-006 | Platform & Tenancy | FO-03, FIN-01 | A read-only hotel can still settle and check out guests already in house. | BR-013 | Must | R1 | fin.payment.post, fo.checkout | Rule: Read-only tenants | an expired hotel with a guest in house who owes money | staff post a payment and check the guest out | both succeed; new bookings and charges are refused with E_READ_ONLY | assert_writable(p_allow_settlement) | 15 | Built+tested
PLT-007 | Platform & Tenancy | SET-03, ADM-01 | Plan limits on rooms, properties and users stop new creation and never delete anything. | BR-002 | Should | R1 | (system) | Rule: Plan limits; A16 | a hotel on a plan of one room | staff add a second room, property or user | the action is refused with E_PLAN_LIMIT; existing data is untouched | limit_rooms, limit_properties, limit_users triggers | 15 | Built+tested
PLT-008 | Platform & Tenancy | (platform console) | Platform staff activate, suspend, change plan or close a hotel by hand, with a reason, and every change is logged. | BR-001 | Must | R1 | platform.billing.manage, platform.tenant.manage | Rule: Read-only tenants; A13 | a hotel whose invoice was paid outside the system | platform staff activate it with a paid-until date | it becomes Active, works again, and the change appears in the subscription history | platform_change_subscription | 15 | Built+tested
PLT-009 | Platform & Tenancy | (platform console) | Platform staff see tenants and subscriptions but no guest, reservation or financial data. | BR-017 | Must | R1 | platform.tenant.manage | Rule: Platform Super Admin | a platform user | they query guests, folios or reservations | they get no rows | row-level security; platform staff have no tenant profile | 15 | Built+tested
PLT-010 | Platform & Tenancy | (platform console) | Time-boxed break-glass support access, with reason, tenant notice and audit entry. | BR-017, BR-018 | Should | R1 | platform.support.access | Rule: Platform Super Admin | a platform user needs to help a hotel | they request support access with a reason | access is limited in time, written to the hotel's audit log and the hotel is told | (not written) | - | Not built
PLT-011 | Platform & Tenancy | (billing page) | A hotel can cancel its own subscription and stays read-only afterwards. | BR-001 | Should | R1 | org.subscription.manage | A13 | a hotel administrator | they cancel the subscription with a reason | status becomes Cancelled and, when no paid period remains, the hotel is read-only | cancel_subscription | 17 | Built+tested
PLT-012 | Platform & Tenancy | (billing page) | Subscription billing through a payment provider (Paystack or Flutterwave). | BR-001 | Should | R1b | org.billing.paymentmethod | A13 | a hotel wants to pay online | they choose a plan and pay | the subscription activates automatically | (pilots are invoiced by hand until then) | - | R1b
ADM-001 | Administration | ADM-01 | A hotel administrator adds staff to the hotel. | BR-017 | Must | R1 | adm.user.manage | Rule: Role assignment | an administrator and a new auth user created by an Edge Function | the administrator registers the user | the user joins the hotel; a person who already belongs to a hotel cannot be taken over | register_invited_user (the Edge Function creates the auth user and sends the invite) | 10, 15 | Built (UI or Edge Function work remains)
ADM-002 | Administration | ADM-02 | Only administrators assign roles, per property or hotel-wide; the last administrator cannot be removed. | BR-017 | Must | R1 | adm.role.assign | Rule: Role assignment | a hotel with one System Administrator | that person is removed or disabled | the change is refused with E_LAST_ADMIN; platform roles can never be assigned by a hotel | assign_role, remove_role, set_user_status | 15 | Built+tested
ADM-003 | Administration | ADM-01 | A disabled user loses all access immediately. | BR-017 | Must | R1 | adm.user.manage | - | a cashier who leaves the company | an administrator disables the user | every action the user tries is refused with E_PERM | set_user_status; grant_level checks profile status | 15 | Built+tested
ADM-004 | Administration | ADM-02 | Custom roles cannot hold more than their creator holds. | BR-017 | Must | R1 | adm.role.manage | Rule: Role assignment | an administrator without payment rights | they add fin.payment.post to a custom role | the change is refused with E_ESCALATION; system roles cannot be edited | role_perm_no_escalation trigger; roles policies | 15 | Built+tested
ADM-005 | Administration | ADM-02 | Limit-based permissions (grant level L) use a per-role amount; no limit means zero. | BR-015, BR-017 | Must | R1 | adm.config.manage | Rule: Limits | a role with level L on discount and a limit of 5,000 | the user applies a discount of 8,000 | the discount waits for approval | approval_limits, approval_limit() | 12 | Built+tested
ADM-006 | Administration | ADM-03 | The audit trail cannot be changed or deleted by anyone, and is visible to permitted roles only. | BR-014, BR-018 | Must | R1 | adm.audit.view | Rule: Immutability, Audit log access | audit events exist | anyone, including the database owner, updates or deletes one | the change is refused with E_IMMUTABLE | audit_events triggers; audit_read policy | 11, 13, 16 | Built+tested
ADM-007 | Administration | (all) | Sensitive actions require a reason and write an audit event with actor, time, before and after. | BR-018 | Must | R1 | (all S permissions) | Rule: Reasons | a sensitive action (cancel, rate override, refund, block, reopen, override condition) | it is performed | a reason is required and an audit event is written | app.audit calls in each function | 12, 13, 14, 15, 17 | Built+tested
ADM-008 | Administration | (bell icon) | Staff get in-app notifications for approvals, tasks and exceptions, and can mark them read. | BR-017 | Should | R1 | (own) | - | an approval is requested | the requester submits it | users holding the approve permission get a notification; each user sees only their own | notifications, notify_permission, notify_user | 16, 17 | Built+tested
ADM-009 | Administration | (exports) | Authorised users export data. | BR-020 | Should | R1 | data.export, rep.export | - | an authorised user | they export a report | a file is produced and the export is audited | (needs an Edge Function or client-side export) | - | Not built
SET-001 | Setup | SET-01 | Property profile can be edited, but the business date and base currency cannot. | BR-002 | Must | R1 | setup.property.manage | Rule: Business date | a property with postings | an administrator edits the profile | name, contact, rollover time and inspection setting change; business date and base currency are refused | column grants on properties | 16 | Built+tested
SET-002 | Setup | SET-02 | Room types with occupancy limits and an overbooking allowance. | BR-004 | Must | R1 | setup.roomtype.manage | - | an administrator | they add a room type | it appears in availability and booking | room_types (direct write with RLS) | 10, 13 | Built+tested
SET-003 | Setup | SET-03 | Room inventory per property; rooms can be retired but never deleted while in use. | BR-004, BR-009 | Must | R1 | setup.room.manage | - | an administrator | they add rooms | they start Ready and Vacant and count towards inventory; condition and occupancy cannot be written by hand | rooms; column grants | 10, 14, 16 | Built+tested
SET-004 | Setup | SET-04 | Rate plans with prices by room type, date range and weekday, and policies for cancellation, no-show and deposit. | BR-004 | Must | R1 | setup.rateplan.manage | A3 | a rate plan with a cancellation rule of one night inside two days | a guest cancels one day before arrival | one night is charged | rate_plans, rate_plan_prices, night_price, policy_fee | 13 | Built+tested
SET-005 | Setup | SET-05 | Tax lines with rate, base (net or net plus prior taxes), applicable revenue groups and a verified flag. | BR-013 | Must | R1 | setup.tax.manage | A11 | service charge 10% then VAT 7.5% on price plus service charge | a charge of 10,000 is posted | tax lines of 1,000 and 825 are posted; inclusive prices solve back to the same net | tax_rates, compute_taxes | 12 | Built+tested
SET-006 | Setup | SET-05 | Charge codes and payment methods per property. | BR-013 | Must | R1 | setup.tax.manage | Rule: Payments in R1 | a property | staff post a charge or a payment | only active codes and methods of that property are accepted | charge_codes, payment_methods | 12 | Built+tested
SET-007 | Setup | SET-05 | Exchange rates per property per day, entered by hand. | BR-013 | Should | R1 | setup.fx.manage | Rule: Multi-currency; A10 | USD at 1,500 | a guest pays USD 10 | the row stores amount, currency, rate 1,500 and a base amount of 15,000; a currency without a rate is refused | set_exchange_rate, fx_rate | 12 | Built+tested
SET-008 | Setup | SET-01 | Inspection can be switched off per property. | BR-011 | Should | R1 | setup.property.manage | Transition: Room Condition Cleaning to Ready | inspection_required is false | an attendant completes a task | the room is Ready at once and the task closes itself | complete_hk_task | 17 | Built+tested
RES-001 | Reservations | RES-01, RES-04 | Availability is calculated per room type and night from sellable rooms less held bookings. | BR-004 | Must | R1 | res.availability.view | Rule: Room condition vs sellability | three standard rooms and three bookings for a night | staff search that night | availability is zero; approved blocks reduce sellable rooms; dirty rooms do not | get_availability, holds_inventory | 13, 14 | Built+tested
RES-002 | Reservations | RES-02 | Create a reservation for one room type and rate plan, priced night by night. | BR-004, BR-007 | Must | R1 | res.create | Transition: Reservation new to Inquiry/Tentative/Confirmed | a room type with a rate | staff create a two-night booking | nights are priced from the rate plan, a folio is opened, and the same idempotency key returns the same booking | create_reservation | 13 | Built+tested
RES-003 | Reservations | RES-02 | A sold-out room type cannot be booked, and occupancy and stay-length limits are enforced. | BR-004, BR-005 | Must | R1 | res.create | - | a sold-out night | staff book it | the booking is refused with E_UNAVAILABLE; too many guests gives E_OCCUPANCY; past arrival gives E_DATES | assert_available (advisory lock per property and room type) | 13 | Built+tested
RES-004 | Reservations | RES-03 | Modify dates, room type, rate plan or guest count before check-in; the stay is repriced and inventory follows. | BR-004 | Must | R1 | res.edit | Transition: Reservation edit | a confirmed booking | staff shorten it by a night | the total is repriced and the night is released; an in-house booking cannot be edited this way | modify_reservation | 13 | Built+tested
RES-005 | Reservations | RES-02, RES-03 | A tentative booking holds inventory until its hold expires, then is released at the next roll; confirming ends the hold. | BR-004 | Must | R1 | res.create, res.edit | Transition: Tentative to Confirmed / Cancelled | a tentative booking with a 1-hour hold | the hold passes and the roll runs | the booking is cancelled with reason 'Hold expired' and inventory is free | create_reservation, confirm_reservation, roll_business_date | 17 | Built+tested
RES-006 | Reservations | RES-03 | Cancel with a reason; the fee follows the rate plan; only a permitted user can waive it. | BR-004, BR-015 | Must | R1 | res.cancel, res.rate.override | Transition: Confirmed to Cancelled | a booking inside the free-cancellation window | staff cancel it | one night's fee is posted to the folio; a cancellation outside the window is free; waiving the fee needs res.rate.override | cancel_reservation | 13 | Built+tested
RES-007 | Reservations | RES-03, FO-01 | No-show can be marked by hand or by the automatic roll, with the fee from the rate plan. | BR-004 | Must | R1 | res.noshow.mark | Transition: Confirmed to No-show; A2 | a confirmed booking whose arrival date is today | staff mark it no-show, or the roll runs | the booking is No-show, the fee is posted once and the room hold is released; a guest not yet due cannot be marked | mark_no_show, no_show_internal, roll_business_date | 13, 14 | Built+tested
RES-008 | Reservations | RES-03 | Reinstate a cancelled or no-show booking when inventory allows. | BR-004 | Should | R1 | res.reinstate | Transition: Cancelled/No-show to Confirmed | a cancelled booking with the room type still available | a manager reinstates it with a reason | it is Confirmed again and its folio reopens; if the type is full it is refused | reinstate_reservation | 13 | Built+tested
RES-009 | Reservations | RES-02 | Rate override needs its own permission and a reason, and is audited. | BR-015, BR-018 | Must | R1 | res.rate.override | Rule: Reasons | a front desk officer without the permission | they set a custom rate | the request is refused; a manager with a reason sets the rate and the override is audited | create_reservation, modify_reservation | 13, 17 | Built+tested
RES-010 | Reservations | RES-02 | A deposit rule on the rate plan sets the deposit required. | BR-013 | Must | R1 | res.deposit.request | Rule: Payments in R1 | a rate plan asking for 50% deposit | a two-night booking is made | the deposit required is half the stay and the guarantee type is deposit | create_reservation | 13 | Built+tested
RES-011 | Reservations | RES-02 | Corporate business is a booking source plus a free-text company name plus a corporate rate plan; no company entity in R1. | BR-007, BR-024 | Must | R1 | res.create | A3 | a booking for a company | staff choose source Corporate and type the company name | the company name is saved with the booking and reports can filter on it | reservations.company_name, rate_plans.is_corporate | 17 | Built+tested
RES-012 | Reservations | RES-02 | A group booking is several one-room reservations sharing a group record. | BR-007 | Should | R1 | res.group.manage | - | a group with a contact and dates | staff create reservations for the group | each reservation links to the group; each room is booked and assigned on its own | group_bookings, reservations.group_id | - | Built (UI or Edge Function work remains)
RES-013 | Reservations | RES-03 | Additional guests and an arrival-ready flag on a booking. | BR-003 | Should | R1 | res.edit | Rule: arrival-ready is a flag | a confirmed booking | staff add a second guest and set arrival-ready | both are saved; arrival-ready never changes the status | set_reservation_guests, set_arrival_ready | 17 | Built+tested
FO-001 | Front Office | FO-01 | Arrivals due today or overdue, with guest, room type, guarantee and assigned room. | BR-006 | Must | R1 | fo.board.view | - | a confirmed booking due today | staff open the board | it appears with the guest's name; after check-in it leaves the list | v_arrivals | 17 | Built+tested
FO-002 | Front Office | FO-01 | In-house guests with room, departure and balance; overdue departures flagged. | BR-006 | Must | R1 | fo.board.view | - | a guest in house | staff open the board | the guest appears with room number and balance | v_in_house | 17 | Built+tested
FO-003 | Front Office | FO-02 | Check-in guards: confirmed booking, arrival date reached, ID recorded, registration accepted, room ready and free, deposit paid. | BR-006, BR-011 | Must | R1 | fo.checkin | Transition: Confirmed to Checked In | a booking due today | staff check the guest in without ID, or into a dirty or occupied room, or without the deposit | each is refused with its own code; with everything in place the reservation is Checked In, the stay In-House and the room Occupied | check_in | 13 | Built+tested
FO-004 | Front Office | FO-02 | Walk-in check-in creates the booking and checks in in one step. | BR-006, BR-007 | Must | R1 | fo.checkin.walkin | Transition: (walk-in) to Checked In | a free ready room | staff check in a walk-in guest | a confirmed walk-in booking is created and the guest is checked in | walk_in_check_in | 13 | Built+tested
FO-005 | Front Office | RES-03, FO-01 | Assign a room before arrival; two overlapping stays can never hold the same room. | BR-005 | Must | R1 | fo.room.assign | Transition: Room Assignment none to Held | a room held for a booking | staff assign it to an overlapping booking | the database refuses with E_ROOM_TAKEN; a room of the wrong type is refused with E_ROOM_TYPE | assign_room; exclusion constraint no_overlapping_room_use | 13 | Built+tested
FO-006 | Front Office | FO-04 | Move a guest to another room; the old room turns dirty with a turnover task; the stay and folio carry over. | BR-006, BR-010 | Must | R1 | fo.roommove | Transition: Room Assignment Active to Ended | a guest in house and a ready room | staff move the guest with a reason | one active room at a time, old room dirty and vacant, new room occupied, task created; a dirty target is refused | move_room | 13 | Built+tested
FO-007 | Front Office | FO-04 | A move to a different room type reprices from tonight; a complimentary upgrade keeps the rate and needs its own permission. | BR-006 | Should | R1 | fo.roommove.complimentary | Transition: complimentary move | a guest booked in a standard room | a manager upgrades them free | the booked rate stays but the night counts against deluxe inventory; a front desk officer is refused | move_room | 13 | Built+tested
FO-008 | Front Office | FO-01, RES-03 | Extend or shorten a stay in house; extension checks inventory, the room and blocks. | BR-006 | Must | R1 | fo.stay.extend | Transition: Stay extension | a guest in house and the room promised to another guest | staff extend the stay | the extension is refused with E_ROOM_TAKEN; a free extension prices the new night; shortening removes unused nights | extend_stay | 13 | Built+tested
FO-009 | Front Office | FO-03 | Check-out needs a zero balance and no credit, or an approved exception; open folios stay open for collection. | BR-006, BR-013 | Must | R1 | fo.checkout, fo.checkout.unsettled.approve | Transition: In-House to Checked Out | a guest who owes money | staff try to check them out | it is refused until a different person approves an exception; then the stay closes, the invoice shows the balance and the folio stays open; a credit balance must be refunded first | check_out, request_unsettled_checkout | 13, 14 | Built+tested
FO-010 | Front Office | FO-03 | Check-out sets the room Dirty and Vacant and creates a turnover task; leaving early releases the unused nights. | BR-010 | Must | R1 | fo.checkout | Transition: Room Condition Ready to Dirty | a guest checks out | the check-out completes | the room is Dirty and Vacant, a turnover task exists, the folio closes and an invoice is issued | check_out, create_turnover_task | 13, 14 | Built+tested
FO-011 | Front Office | FO-03 | Undo a check-out on the same business date. | BR-006 | Should | R1 | fo.checkout.reverse | Transition: Checked Out to Checked In | a guest checked out today and the room not yet being cleaned | a manager undoes it with a reason | the guest is in house, the room occupied, the task cancelled and the folio open; a front desk officer is refused | undo_checkout | 13 | Built+tested
FO-012 | Front Office | FO-02 | Void a check-in on the same business date when no charges are posted. | BR-006 | Should | R1 | fo.checkout.reverse | Transition: Stay In-House to Voided | a check-in made in error today | a manager voids it with a reason | the stay is Voided, the booking Confirmed, the room vacant and held; the guest can be checked in again | void_check_in | 17 | Built+tested
FO-013 | Front Office | ROOM-01 | Room board shows each room as occupied, vacant by condition, out of order or out of service. | BR-009 | Must | R1 | room.view | Rule: Room condition vs sellability | a guest in a room | staff open the room board | the room shows occupied | v_room_board | 17 | Built+tested
GST-001 | Guests | GST-01, GST-02 | One guest profile per person across stays; search by name, phone, email or ID number. | BR-003, BR-008 | Must | R1 | guest.view, guest.create, guest.edit | - | guests exist | front desk searches by surname | the guest is found; a role without guest.view finds nothing | guests, search_guests | 15 | Built+tested
GST-002 | Guests | GST-02 | ID documents are stored apart and shown only to roles that may see them. | BR-017 | Must | R1 | guest.idocs.view | - | a recorded passport number | a reservation officer opens the guest | they see the profile but no ID documents | guest_documents policies | 17 | Built+tested
GST-003 | Guests | GST-02 | Personal data never appears in audit records; only the names of changed fields do. | BR-018 | Must | R1 | - | Rule: Personal data and the ledger | a phone number is changed | the audit trail is read | it says the phone changed, not what the number was | audit_change_pii | 15 | Built+tested
GST-004 | Guests | GST-02 | Merge duplicate guest profiles; history moves to the kept profile. | BR-003 | Should | R1 | guest.merge | - | two profiles for one person | a manager merges them with a reason | reservations and folios point to the kept profile and the duplicate is emptied | merge_guests | 15 | Built+tested
GST-005 | Guests | GST-02 | Anonymise a guest on request; the ledger and stay history stay intact. | BR-003, BR-014 | Should | R1 | guest.merge | Rule: Personal data and the ledger | a guest with no current or upcoming stay | a manager anonymises them | name, contact and documents are removed and cannot be restored from the app; reservations remain | anonymise_guest | 15 | Built+tested
GST-006 | Guests | GST-02 | Feedback and complaints logged against a guest. | BR-008 | Should | R1 | guest.complaint.manage | - | a guest complaint | staff log it | it is saved with the guest and shown on the profile | guest_feedback (direct write with RLS) | - | Built (UI or Edge Function work remains)
ROOM-001 | Rooms | ROOM-01, ROOM-02 | Room condition and occupancy are separate, are set only by the system or a controlled action, and cannot be written by hand. | BR-009 | Must | R1 | room.view | Rule: Room condition vs sellability | any user | they try to update condition or occupancy directly | the update is refused with permission denied | column grants; rooms | 14, 16 | Built+tested
ROOM-002 | Rooms | ROOM-03 | Out-of-order and out-of-service blocks; a request from maintenance needs approval, an approver's own request does not. | BR-012 | Must | R1 | room.block.request, room.block.approve, room.block.release | Transition: Room Block | a maintenance officer requests a block | a manager approves it | the room leaves availability for those nights; a requested block does not; releasing returns it | request_room_block, decide_approval, release_room_block | 14 | Built+tested
ROOM-003 | Rooms | ROOM-03 | A block cannot cover a night a guest is assigned, and cannot oversell the room type. | BR-005, BR-012 | Must | R1 | room.block.request | - | a room assigned to a guest or the last room of a type | staff block it | the block is refused with E_ROOM_TAKEN or E_OVERSOLD | request_room_block, assert_not_oversold | 14, 17 | Built+tested
ROOM-004 | Rooms | ROOM-02 | A supervisor can override a room's condition with a reason; it is audited. | BR-018 | Should | R1 | room.status.override | Rule: Reasons | a dirty room a manager has inspected | the manager marks it ready with a reason | the room is Ready and the override is in the audit trail; front desk is refused | set_room_condition | 13, 14 | Built+tested
HK-001 | Housekeeping | HK-01 | Check-out and room moves create a turnover task; the board lists open tasks. | BR-010 | Must | R1 | hk.board.view | Transition: Ready to Dirty | a guest checks out | the check-out completes | a pending turnover task exists for the room; an older unfinished task is superseded | create_turnover_task, v_hk_board | 13, 14 | Built+tested
HK-002 | Housekeeping | HK-01, HK-02 | Assign, start and complete cleaning tasks; an attendant sees only their own tasks. | BR-010 | Must | R1 | hk.task.assign, hk.task.execute | Transition: Dirty to Cleaning to Awaiting Inspection | a pending task | a supervisor assigns it and the attendant starts and completes it | the room goes Cleaning then Awaiting Inspection; an attendant cannot start another person's task | assign_hk_task, start_hk_task, complete_hk_task | 14, 17 | Built+tested
HK-003 | Housekeeping | HK-03 | Inspection passes to Ready or fails with a reason and goes to rework. | BR-011 | Must | R1 | hk.inspect | Transition: Awaiting Inspection to Ready / Cleaning | a completed task | the inspector fails it with a reason | the room is Dirty, the task is in rework and the attendant is notified; a pass makes it Ready | inspect_hk_task | 14 | Built+tested
HK-004 | Housekeeping | HK-03 | Nobody inspects their own cleaning. | BR-015 | Must | R1 | hk.inspect | Rule: Separation of duties | a supervisor who cleaned a room | they inspect it | it is refused with E_SOD | inspect_hk_task | 14 | Built+tested
HK-005 | Housekeeping | HK-01 | Stayover cleaning tasks are planned at the roll for guests staying on. | BR-010 | Should | R1 | (system) | Transition: stayover; Rule: Business date | a guest in house who stays another night | the roll runs | a stayover task exists for the new day; a departing guest gets none | roll_business_date | 14 | Built+tested
HK-006 | Housekeeping | (lost & found) | Lost and found items are logged and tracked to return or disposal. | BR-013 | Should | R1 | hk.lostfound.manage | - | a found item | housekeeping logs it | it is saved with room, date and status | lost_found_items (direct write with RLS) | 16 | Built+tested
MNT-001 | Maintenance | MNT-01, MNT-02 | Tickets move from open to assigned, in progress, waiting, resolved and closed; waiting needs a reason. | BR-012 | Must | R1 | mnt.ticket.create, mnt.ticket.manage, mnt.ticket.work | States: Maintenance Ticket | a ticket | it is assigned, started, paused with a reason, resumed and resolved | each step follows the allowed path and a ticket assigned to someone else cannot be started by another person | create_ticket, assign_ticket, start_ticket, wait_ticket, resolve_ticket | 14 | Built+tested
MNT-002 | Maintenance | MNT-02 | The person who resolved a ticket cannot close it; closing releases its room block. | BR-015, BR-012 | Must | R1 | mnt.ticket.close | Rule: Separation of duties | a resolved ticket with a room block | its resolver tries to close it, then a supervisor does | the first is refused with E_SOD; the second closes it and releases the block | close_ticket | 14 | Built+tested
MNT-003 | Maintenance | MNT-02 | Tickets can be reopened or cancelled, each with a reason. | BR-012 | Should | R1 | mnt.ticket.manage, mnt.ticket.cancel | States: Maintenance Ticket | a resolved ticket | a maintenance officer reopens it or cancels it | the status changes and the reason is audited; housekeeping cannot cancel | reopen_ticket, cancel_ticket | 17 | Built+tested
SVC-001 | Guest Service | FO-01 | Guest requests are captured, assigned, progressed and completed. | BR-006 | Should | R1 | svc.request.create, svc.request.manage | Workflow WF05 | a guest in house | staff log a request and it is assigned, started and completed | it is tied to the guest's room and finishes once | create_service_request, assign_service_request, start_service_request, complete_service_request | 17 | Built+tested
SVC-002 | Guest Service | FO-01, FIN-01 | A chargeable request posts its charge, with tax, to the folio when completed. | BR-013 | Should | R1 | svc.request.manage, fin.charge.post | Workflow WF05 | a chargeable laundry request of 3,000 | it is completed | 3,000 plus tax is posted once to the guest's folio | complete_service_request | 17 | Built+tested
FIN-001 | Finance | FIN-01 | Charges post with their tax lines; prices can include or exclude tax; the remainder of a rounding goes on the last tax line. | BR-013 | Must | R1 | fin.charge.post | Rule: Business date | service charge 10% and VAT 7.5% | a charge of 10,000 or an inclusive 11,825 is posted | the folio owes 11,825 with a net of 10,000 either way | post_charge, compute_taxes, insert_with_tax | 12 | Built+tested
FIN-002 | Finance | FIN-01 | Payments and deposits are recorded against a folio with a method; payments are taken outside the system in R1. | BR-013 | Must | R1 | fin.payment.post, fin.deposit.take | Rule: Payments in R1 | a folio with a balance | staff record a cash payment or a deposit | the balance falls; a role without the matching permission is refused | post_payment | 12 | Built+tested
FIN-003 | Finance | FIN-01 | Foreign-currency postings store the amount, currency, exchange rate and base amount. | BR-013 | Should | R1 | fin.payment.post | Rule: Multi-currency | USD 10 at 1,500 | it is posted | the row shows the rate and 15,000 in the base currency; the amount must respect the currency's decimals | insert_txn, fx_rate | 12 | Built+tested
FIN-004 | Finance | FIN-01 | A discount within the user's limit posts at once; above the limit it waits for an approver who is not the requester. | BR-015 | Must | R1 | fin.discount.apply, fin.discount.approve | Rule: Limits; Separation of duties | a front desk limit of 5,000 | they apply 3,000 then 8,000 | the first posts; the second is pending, does not change the balance and can be approved or rejected (with a reason) by a manager | apply_discount, decide_approval | 12 | Built+tested
FIN-005 | Finance | FIN-01 | Adjustments, reversals and refunds always need a second person and stay within the approver's limit. | BR-015 | Must | R1 | fin.adjust.post, fin.adjust.approve, fin.reverse.post, fin.refund.post, fin.refund.approve | Rule: Separation of duties, Limits | an adjustment of 50,000 requested by a cashier | a manager with a 20,000 limit approves | it is refused with E_LIMIT; a senior approver can; nobody approves their own request | request_adjustment, request_reversal, request_refund, decide_approval; check constraint approver_is_not_requester | 12 | Built+tested
FIN-006 | Finance | FIN-01 | A posted transaction is never edited or deleted; corrections are linked reversal, adjustment or refund rows. | BR-014, BR-015 | Must | R1 | - | Rule: Immutability | a posted charge | anyone, including the database owner, changes or deletes it | the change is refused with E_IMMUTABLE; a reversal posts a linked row (with its tax lines) and a charge reverses only once | txn_guard triggers; request_reversal | 12 | Built+tested
FIN-007 | Finance | FIN-01 | A refund cannot exceed the credit on the folio. | BR-015 | Must | R1 | fin.refund.post | - | a folio with a small credit | staff request a bigger refund | it is refused with E_REFUND_LIMIT; a refund within the credit is approved and pays out | request_refund | 12 | Built+tested
FIN-008 | Finance | FIN-01 | Repeating the same request cannot double post (idempotency keys). | BR-013 | Must | R1 | - | Rule: Offline-ready design; A12 | a charge posted with a key | the same request arrives again | the second returns the first and the balance is unchanged | idempotency_key unique per tenant | 12, 13 | Built+tested
FIN-009 | Finance | FIN-01 | Move a posted charge, with its tax, to another folio of the same booking; revenue does not change. | BR-013 | Should | R1 | fin.folio.transfer | - | a charge on the guest folio | a manager transfers it to a company folio | the target owes the charge and tax, the source is relieved, the total is unchanged and the charge moves once | transfer_transaction | 12 | Built+tested
FIN-010 | Finance | FIN-01 | Split folios per reservation. | BR-013 | Should | R1 | fin.folio.split | - | a reservation | staff add a Company folio | charges can be posted to either folio and check-out settles both | split_folio | 12, 13 | Built+tested
FIN-011 | Finance | FIN-01 | A folio closes only at a zero balance and reopens only for the accountant with a reason; a closed folio takes no postings. | BR-013, BR-015 | Must | R1 | fin.invoice.issue, fin.folio.reopen | Rule: Reasons | a settled folio | it is closed and then a posting is attempted | the posting is refused with E_FOLIO_CLOSED; reopening needs the permission and a reason and is audited | close_folio, reopen_folio | 12 | Built+tested
FIN-012 | Finance | FIN-01, FO-03 | Invoices and receipts are numbered documents built from posted rows; they cannot be changed once issued. | BR-013 | Must | R1 | fin.invoice.issue | - | a settled folio | an invoice is issued | the total, tax and balance match the folio and the invoice cannot be edited; interim receipts have their own number series | issue_invoice | 12, 17 | Built+tested
FIN-013 | Finance | FIN-01 | Balances are calculated from posted rows and never stored; pending approvals do not change them. | BR-013 | Must | R1 | fin.folio.view | Rule: Immutability | a pending discount | the balance is read | it is unchanged until the approval posts | v_folio_balances | 12 | Built+tested
FIN-014 | Finance | FIN-01 | Every posting takes the open business date, and a past date is refused. | BR-013 | Must | R1 | - | Rule: Business date | a posting for a past date | it is inserted | it is refused with E_DATE | txn_guard | 12 | Built+tested
FIN-015 | Finance | FIN-01 | Folio visibility follows the role: managers see all folios, a reservation officer sees only those of their own bookings. | BR-017 | Must | R1 | fin.folio.view | Own-record scope | a reservation officer | they read a colleague's folio | they see nothing; they can still take a deposit | can_see_folio | 12 | Built+tested
FIN-016 | Finance | FIN-02 | Cashier shifts and reconciliation by cashier, shift and method. | BR-016 | Should | R2 | fin.shift.manage, fin.shift.reconcile | - | a cashier shift | the shift is closed | payments reconcile by method | (not in R1) | - | R1b
DAY-001 | Business Date | (system) | The business date rolls automatically at each property's cut-off time. | BR-019 | Must | R1 | audit.businessdate.view | Rule: Business date; A2 | a property whose cut-off has passed | the scheduler runs | the date advances one day, up to three days per run; the roll is logged | roll_business_date, run_due_rollovers (pg_cron) | 14 | Built+tested
DAY-002 | Business Date | (system) | At the roll, each guest in house is charged the night's room rate and tax exactly once. | BR-013 | Must | R1 | (system) | Rule: Business date | two guests in house | the roll runs | each folio gets one room charge for the closing date, with tax; running it again for the same night cannot repeat it | roll_business_date; idempotency keys room:<reservation>:<date> | 14 | Built+tested
DAY-003 | Business Date | (system) | A guest still in house past departure is charged and extended a night if the room allows; otherwise managers are told. | BR-013 | Should | R1 | (system) | - | a guest due out today who is still in house | the roll runs | the departure moves one day and the night is charged | roll_business_date | 14 | Built+tested
DAY-004 | Business Date | (system) | A failed roll changes nothing and notifies managers; other properties are not blocked. | BR-013 | Must | R1 | audit.businessdate.view | - | a property whose roll fails | the scheduler runs | its date is unchanged and managers get a notification | run_due_rollovers | 17 | Built+tested
DAY-005 | Business Date | FIN-03 | Night audit gates the roll from R2. | BR-016 | Should | R2 | audit.night.run | A2 | R2 | - | - | (not in R1) | - | R1b
DAY-006 | Business Date | (system) | A same-day arrival and departure: decide whether a night or day-use charge applies. | BR-013 | Should | R1 | (decision) | - | a guest checks in and out on the same business date | they leave before the roll | today no room charge is made; the desk can post a manual charge | check_out | 13 | Decision needed
RPT-001 | Reporting | DASH-01, REP-01 | Occupancy, ADR and RevPAR use one definition: rooms sold over rooms available (out-of-order rooms excluded), revenue net of tax. | BR-019 | Must | R1 | dash.view_exec, rep.ops.view | KPI Dictionary | a closed day | management opens the KPI view | occupancy, ADR and RevPAR equal sold, revenue and available as defined; tax is shown apart | daily_stats, v_kpi_daily | 14 | Built+tested
RPT-002 | Reporting | DASH-02 | Live operations views: arrivals, in-house, room board, housekeeping board. | BR-006, BR-019 | Must | R1 | dash.view_ops | - | activity in the hotel | staff open the operations dashboard | the views return only rows the user may see | v_arrivals, v_in_house, v_room_board, v_hk_board | 17 | Built+tested
RPT-003 | Reporting | REP-01, REP-02 | Every reported figure traces to ledger rows or operational records. | BR-020 | Must | R1 | rep.ops.view, rep.fin.view | - | a daily figure | an auditor recomputes it from folio_transactions | the figures agree | daily_stats computed from folio_transactions | 14 | Built+tested
RPT-004 | Reporting | REP-01, REP-02 | Report screens (occupancy trend, revenue by group, outstanding balances, cancellation and no-show rates). | BR-019 | Must | R1 | rep.ops.view, rep.fin.view | KPI Dictionary | a date range | a manager opens a report | the numbers match the KPI definitions | (views for cancellation rate, ALOS and outstanding balances still to add) | - | Built (UI or Edge Function work remains)
NFR-001 | Non-functional | (all) | Every table has row-level security and tenant_id; security definer functions pin their search path. | BR-017 | Must | R1 | - | Rule: Tenant isolation | a migration adds a table or function | the test suite runs | it fails if RLS, tenant_id or search_path is missing | structure tests | 16 | Built+tested
NFR-002 | Non-functional | (all) | The browser can write directly only to plain configuration tables; ledger, reservations, stays, tasks and blocks change only through functions. | BR-014, BR-017 | Must | R1 | - | Rule: Immutability | any user | they write to a ledger or state table | permission denied; the list of directly writable tables is asserted by a test | 20260928001100_grants.sql | 16 | Built+tested
NFR-003 | Non-functional | (all) | Create actions accept client-generated ids and idempotency keys so an offline queue can be added later. | BR-001 | Should | R1 | - | Rule: Offline-ready design; A12 | a repeated create request | it arrives twice | only one record exists | idempotency keys; client ids allowed on insert | 12, 13 | Built+tested
NFR-004 | Non-functional | (all) | Money uses fixed decimals per currency (naira 2, CFA franc 0), never floating point. | BR-013 | Must | R1 | - | A10 | an amount with too many decimals | it is posted | it is refused with E_PRECISION | numeric(20,4), currencies.decimals | 12 | Built+tested
NFR-005 | Non-functional | (all) | Business date and cut-off follow the property's timezone. | BR-019 | Must | R1 | - | A2 | a property in Lagos | it is created just before or after cut-off | the business date is the local hotel day, not the server's day | local_business_date | 14, 17 | Built+tested

## BR Coverage
BR | Domain | Business requirement | Priority | Release | Requirement ids | Count | Coverage
BR-001 | Enterprise | One controlled system of record for hotel operations. | Must | R1 | PLT-001, PLT-005, PLT-008, PLT-011, PLT-012, NFR-003 | 6 | Covered in R1
BR-002 | Enterprise | Property-level configuration and future multi-property operation. | Must | R1 | PLT-001, PLT-003, PLT-004, PLT-007, SET-001 | 5 | Covered in R1
BR-003 | Enterprise | A single guest identity across reservations and stays. | Must | R1 | RES-013, GST-001, GST-004, GST-005 | 4 | Covered in R1
BR-004 | Reservations | Sellable room inventory for any requested stay period. | Must | R1 | SET-002, SET-003, SET-004, RES-001, RES-002, RES-003, RES-004, RES-005, RES-006, RES-007, RES-008 | 11 | Covered in R1
BR-005 | Reservations | Prevent conflicting physical room assignments. | Must | R1 | RES-003, FO-005, ROOM-003 | 3 | Covered in R1
BR-006 | Front Office | Arrivals, departures, in-house guests and room assignments from a focused interface. | Must | R1 | FO-001, FO-002, FO-003, FO-004, FO-006, FO-007, FO-008, FO-009, FO-011, FO-012, SVC-001, RPT-002 | 12 | Covered in R1
BR-007 | Front Office | Walk-in, direct, corporate, group and future channel bookings. Reworded (A3): corporate is a booking source, a free-text company name and a corporate rate plan. No company entity. | Must | R1 | RES-002, RES-011, RES-012, FO-004 | 4 | Covered in R1
BR-008 | Guest | Guest history accessible to authorised staff across stays. | Must | R1 | GST-001, GST-006 | 2 | Covered in R1
BR-009 | Rooms | Commercial availability kept apart from operational room condition. | Must | R1 | SET-003, FO-013, ROOM-001 | 3 | Covered in R1
BR-010 | Housekeeping | Check-out triggers the room turnover workflow. | Must | R1 | FO-006, FO-010, HK-001, HK-002, HK-005 | 5 | Covered in R1
BR-011 | Housekeeping | Only rooms meeting readiness rules are normally assignable for arrival. | Must | R1 | SET-008, FO-003, HK-003 | 3 | Covered in R1
BR-012 | Maintenance | Maintenance issues that affect sellability can block the room. | Must | R1/R2 | ROOM-002, ROOM-003, MNT-001, MNT-002, MNT-003 | 5 | Covered in R1
BR-013 | Finance | All financial activity is a traceable folio transaction. | Must | R1 | PLT-006, SET-005, SET-006, SET-007, RES-010, FO-009, HK-006, SVC-002, FIN-001, FIN-002, FIN-003, FIN-008, FIN-009, FIN-010, FIN-011, FIN-012, FIN-013, FIN-014, DAY-002, DAY-003, DAY-004, DAY-006, NFR-004 | 23 | Covered in R1
BR-014 | Finance | Financial transactions are never silently deleted. | Must | R1 | ADM-006, GST-005, FIN-006, NFR-002 | 4 | Covered in R1
BR-015 | Finance | Refunds, reversals, discounts and adjustments keep an audit trail. | Must | R1 | ADM-005, RES-006, RES-009, HK-004, MNT-002, FIN-004, FIN-005, FIN-006, FIN-007, FIN-011 | 10 | Covered in R1
BR-016 | Finance | Reconcile payments by cashier, shift, method and business date. | Must | R2 (method and date in R1) | FIN-016, DAY-005 | 2 | Partly covered in R1
BR-017 | Security | Users act only within their role and property scope. | Must | R1 | PLT-002, PLT-003, PLT-009, PLT-010, ADM-001, ADM-002, ADM-003, ADM-004, ADM-005, ADM-008, GST-002, FIN-015, NFR-001, NFR-002 | 14 | Covered in R1
BR-018 | Security | Sensitive actions record actor, time, action, before and after values, and reason. | Must | R1 | PLT-010, ADM-006, ADM-007, RES-009, GST-003, ROOM-004 | 6 | Covered in R1
BR-019 | Reporting | Common KPI definitions for occupancy, ADR, RevPAR, revenue and status. | Must | R1 | DAY-001, RPT-001, RPT-002, RPT-004, NFR-005 | 5 | Covered in R1
BR-020 | Reporting | Reports trace to the underlying records. | Must | R1 | ADM-009, RPT-003 | 2 | Covered in R1
BR-021 | F&B | Restaurant and bar orders posting room charges. | Should | R2 |  | 0 | Later release
BR-022 | Inventory | Stock receipts, issues, transfers, wastage and counts. | Should | R2 |  | 0 | Later release
BR-023 | Procurement | Request, approval, PO and receipt controls. | Should | R2 |  | 0 | Later release
BR-024 | Commercial | Corporate and group business as structured commercial accounts. | Should | R2 (R1 covers source, name, rate plan, group record) | RES-011 | 1 | Partly covered in R1
BR-025 | Events | Venue, services, accommodation and billing for events. | Should | R2 |  | 0 | Later release
BR-026 | Workforce | Staff records and schedules for assignment. | Should | R2 |  | 0 | Later release
BR-027 | Digital | Guest self-service for booking and stay. | Could | R3 |  | 0 | Later release
BR-028 | Distribution | Channel sync of inventory and rates. | Could | R3 |  | 0 | Later release
BR-029 | Loyalty | Loyalty and guest segmentation. | Could | R3 |  | 0 | Later release
BR-030 | AI | AI-assisted analysis within authorised controls. | Could | R4 |  | 0 | Later release

## Decisions
Ref | Decision or question | State
A1 | Multi-tenant product for many hotels. | Confirmed
A2 | Business date rolls automatically in R1. Night audit and cashier shift come in R2. | Confirmed
A3 | No Company entity. Corporate is a source, a free-text company name and a corporate rate plan. BR-007 reworded. | Confirmed
A10 | Nigeria first. NGN base currency. Multi-currency with recorded FX rate. Payments are taken outside the system. | Confirmed
A11 | Tax seed (10% service charge, 7.5% VAT on net plus prior, state levy 0%) is unverified. | Open: accountant to confirm
A12 | Online only in R1. Client ids and idempotency keys keep the door open for offline. | Confirmed
A13 | Self-service signup with a 30-day trial. Billing integration is R1b. Pilots are invoiced by hand. | Confirmed
A14 | Cloud hosting. Provider and region not chosen. Nearest Supabase region is Frankfurt. | Open: pick region
A16 | Plans are configuration. Proposed: 30-day trial and room-count tiers (starter 20, standard 60, pro 150, enterprise unlimited). Unpriced. | Open: pick plans and prices
DAY-006 | Same-day arrival and departure: charge a night, a day-use rate, or nothing. | Open: decide
Fees | Cancellation and no-show fee charge codes are non-taxable in the seed. | Open: accountant to confirm
Ops | Enable pg_cron in Supabase and schedule app.run_due_rollovers() every 5 minutes. Run the subscription clock daily. | Open: setup step

## Build Gaps
ID | Item | Type | Work remaining
PLT-010 | Break-glass support access | Not built | Schema and RPC for time-boxed access with reason, tenant notice and audit.
ADM-009 | Data exports | Not built | Export RPCs or Edge Function with permission check and audit entry.
ADM-001 | Invite staff | Edge Function | Function creates the auth user, then calls register_invited_user.
RES-012 | Group booking UI | UI | Backend done. UI to create several one-room reservations under one group.
GST-006 | Feedback and complaints UI | UI | Backend done. UI needed.
RPT-004 | Report views | Views | Add views for cancellation rate, ALOS and outstanding balances.
PLT-012 | Subscription billing | R1b | Paystack or Flutterwave integration.
FIN-016 | Cashier shifts | R1b/R2 | Shift open, close and reconcile.
DAY-005 | Night audit gate | R1b/R2 | Audit must pass before the date rolls.